CONCEPT NOTE FemSaidia Kenya Femicide Intelligence Platform · Safety Tools · Community Action Community Media Trust · Victor Ombonya, Lead Developer · May 2026

Ending femicide through data, technology and community agency

1.  BACKGROUND AND PROBLEM STATEMENT

Kenya is experiencing a femicide crisis of documented severity. A woman is killed every 47 hours. Since 2014, over 600 cases have been reported across media, civil society organisations and police records — yet fewer than 3% have resulted in a conviction, and 83% of cases never reach prosecution. The problem is not the absence of laws. Kenya has the Sexual Offences Act, the Protection Against Domestic Violence Act 2015, and obligations under CEDAW, the Maputo Protocol and the Beijing Platform for Action. The problem is systemic failure at every stage — data, investigation, prosecution, survivor support and public accountability.

Three specific gaps drive this failure:

- No centralised, verified, publicly accessible femicide database. Cases are reported sporadically across media, police stations and CSOs. Policymakers, advocates and researchers have been operating without a shared evidence base.

- No digital safety tools designed specifically for women at risk in Kenya. Existing safety apps require smartphones and internet access, putting them out of reach for women in rural areas, abusive households or low-income settings. No USSD shortcode has ever been built specifically for femicide-risk scenarios.

- No ecosystem coordination infrastructure. Government, CSOs, legal aid organisations, media and donors respond in silos. No shared platform connects their efforts, aligns their data or amplifies their collective impact.

FemSaidia Kenya was built in direct response to these three gaps.

2.  THE SOLUTION — AN INTEGRATED SIX-TOOL ECOSYSTEM

FemSaidia Kenya is an integrated digital ecosystem of six connected tools that addresses the femicide crisis simultaneously at the intelligence, immediate safety and universal access levels. All three tiers are built, deployed and live.

Tool 1: FemSaidia Kenya — femsaidiakenya.org

A femicide intelligence and coordination platform, invite-gated for safety, serving a growing network of civil society organisations, legal aid providers, data researchers and gender justice advocates across Kenya. Key components:

- Live Case Tracker:  35 verified femicide cases with detailed justice status, county breakdown, perpetrator relationship data and a justice funnel showing exactly where cases disappear from the system. Cases are manually verified by the Community Media Trust admin team and sourced from NGEC reports, court records, news media and community documentation.

- Resource Library:  27 verified resources including datasets, legal guides, research reports and media content — filterable by category and year.

- Red Flag Profiles:  A community-sourced database allowing submission of profiles of known perpetrators. Includes a counter-report mechanism and social sharing.

- Survival Guide:  Evidence-based safety protocols covering immediate danger, online dating safety, intimate partner escalation, leaving safely, and law enforcement escalation — adapted specifically for the Kenyan context.

- Community Petition:  A live, Supabase-backed petition with four concrete demands to the Kenyan government. Real-time signature counter.

- Socials & Sentiment:  A Misogyny Index that scores online GBV sentiment daily, powered by an RSS scanner that classifies Kenyan media content in real time.

- CSO Network:  12 critical stakeholder organisations whose participation enables the platform to fulfil its mandate.

Tool 2: hepa — hepa.femsaidiakenya.org

A smartphone safety app built specifically for women at risk of intimate partner violence. hepa is designed with a critical safety feature: it is disguised as a fully functional iOS-style calculator on the phone home screen. The app name is "Calculator". An abuser who picks up the phone sees a standard calculator — indistinguishable from the native app.

To access hepa, the user holds the = button for three seconds, triggering a reveal animation. Once inside, hepa provides:

- Panic button:  One tap sends a precise GPS location to a pre-set trusted contact via WhatsApp and SMS, and displays an immediate 999 call button.

- Shake-to-alert:  The phone can be shaken to trigger the same panic alert — activating the safety response without any screen interaction.

- Check-in timer:  A countdown that, if not cancelled, automatically fires a WhatsApp alert to the trusted contact with the user's last known location.

- Offline survival guide:  Four safety protocol sections available without internet: immediate danger response, online dating safety, leaving safely, and police escalation.

- Emergency contacts:  One-tap dial for police, DCI Gender Desk, GVRC, Usikimye, FIDA Kenya and Kituo Cha Sheria.

- Privacy by design:  No account required, no registration, no data stored on any server. Everything is stored locally on the user's device.

Tool 3: Salmin USSD Shortcode — *384*89056#

A bilingual (Swahili/English) USSD shortcode accessible from any mobile phone, on any network, without internet or data. The shortcode reaches women who do not own smartphones, live in areas with only 2G connectivity, or cannot safely access a web application. Cost to user: Ksh 1.25 per session.

The USSD menu provides: emergency contacts with one-dial access, safety protocols for immediate danger, protocols for leaving an abusive partner, guidance on what to do when police dismiss a report, and incident reporting pathways. The backend is deployed on Supabase Edge Functions with Africa's Talking as the telecom provider. A production shortcode application has been submitted and is pending activation.

Tool 4: Red Flag — redflag.femsaidiakenya.org

A tri-lingual safety-intelligence PWA, now available in English, Kiswahili and Sheng. Four archetypes — The Naive, The Precocious, The All-In and The On/Off — deliver tailored red flags, protective measures and survivor voices. JiJue (know yourself), JiTume (take action — the ecosystem around her) and LindaLinda (community safety norms), alongside a curated We Remember memorial and a community-verified perpetrator database.

Tool 5: Itika — itika.femsaidiakenya.org

A verified First Responder Network — the community layer between a distress signal and the police. A hepa panic, a check-in-timer expiry or a Red Flag SOS fires an instant, county-routed push notification to trained, vetted responders (boda-boda riders, community health workers, SRHR advocates, faith leaders) who reach a survivor within minutes, accompany her and refer her onward.

Tool 6: SaInt — saint.femsaidiakenya.org

The intelligence and fundraising desk (Saidia Intelligence). A live field-intelligence dashboard — Misogyny Index, case counts and tech-facilitated GBV — a Claude-powered synthesis brief, ThinkTank projects mapped to the SDGs and the Maputo Protocol, downloadable Intel Briefs and partnership pathways for funders.

3.  CRITICAL STAKEHOLDERS

The following organisations (not exhaustive) are critical stakeholders whose participation enables FemSaidia Kenya to fulfil its mandate. They represent civil society, data and research, legal and institutional sectors.

| Civil Society & Advocacy | Data, Research & Media | Legal, Government & Institutional |
| --- | --- | --- |
| Usikimye (Kenya) FIDA Kenya COVAW GVRC Kenya VOCAL Africa The Social Justice League Amnesty International Kenya Coalition on Violence Against Women | Africa Data Hub KICTANet Femicide Count Kenya Nation Africa Standard Media Group Citizen Digital NTV Kenya Equal Measures 2030 | Law Society of Kenya NGEC ODPP DCI Gender Desk Ministry of Gender IPOA The Donor Community |

4.  IMPLEMENTATION TIMELINE

| May 2026 | Platform fully built and live. 35 verified cases in database. hepa PWA deployed at hepa.femsaidiakenya.org. USSD backend live on Supabase Edge Functions. Production shortcode application submitted to Africa's Talking. |
| --- | --- |
| July 2026 | Production USSD shortcode activated. Live on Safaricom, Airtel and Telkom Kenya networks. Stakeholder onboarding begins — invitations to CSO partners, legal aid organisations and data partners. |
| 19 August 2026 | SOFT LAUNCH — Aligned with the Making All Spaces Safe (MASS) Digital Safety Campaign. Formal unveiling to stakeholders, media briefing, initial data seeding from stakeholder organisations. hepa download campaign begins. |
| Sep–Oct 2026 | Monitoring and data collection phase. Usage analytics, USSD session logs, hepa installs and case tracker updates compiled. Stakeholder feedback gathered. Refinements deployed. |
| 25 November 2026 | FULL PUBLIC LAUNCH — International Day for the Elimination of Violence Against Women. National media campaign. Government and CSO briefings. Launch of formal funding partnerships. |
| Q1–Q2 2027 | National scale-up — Itika first-responder recruitment and verification; rollout across all 47 counties; CSO partnerships and automated intelligence. |
| Q3–Q4 2027 | Sustainability — government data-sharing MOU, institutional funding secured, team expanded. Close of the 18-month operational period (November 2027). |

5.  BUDGET AND FUNDING REQUEST

Community Media Trust requests funding support for the 18-month operation and scale of the FemSaidia Kenya ecosystem. The platform has been fully developed and is live. Funding will cover operational sustainability, scale-up, staffing and communications — not development risk.

The platform is already built and deployed — this is not development funding. The full 18-month operational and scale budget is USD 110,000 (≈ Ksh 14.3 million), covering production USSD operations, a national Itika first-responder network, the research, verification and data team, hosting and infrastructure, community outreach and communications.

| Budget Line | USD | KSH |
| --- | --- | --- |
| Salmin USSD operations (Africa’s Talking) | $12,000 | 1.56M |
| Itika First Responder Network (training & coordination) | $18,000 | 2.34M |
| Platform hosting & infrastructure (Vercel + Supabase) | $8,000 | 1.04M |
| Research, verification & data team | $30,000 | 3.9M |
| Community outreach & CSO partnerships | $17,000 | 2.21M |
| Communications & media intelligence | $15,000 | 1.95M |
| Organisational management & admin | $10,000 | 1.3M |
| TOTAL — 18-month budget | $110,000 | Ksh 14.3M |

Funding is sought from UN/AU agencies (UNFPA, UN Women), embassy small grants programmes (EU Delegation, FCDO, SIDA, Dutch Embassy, US Embassy), the Kenyan government through NGEC, and technology for good funds (Google.org, Omidyar Network Africa, Ford Foundation). Community Media Trust is open to phased or multi-donor arrangements.

6.  ABOUT COMMUNITY MEDIA TRUST

Community Media Trust is a registered organisation based in Nairobi, Kenya, working at the intersection of civic technology, public interest media and gender justice. The organisation builds digital infrastructure that amplifies marginalised voices, holds power accountable and equips communities with tools to protect themselves.

FemSaidia Kenya — including hepa, RedFlag, Itika, SaInt and Salmin — was developed by Community Media Trust in response to a documented crisis. Victor Ombonya, Executive Director of Community Media Trust, served as Lead Developer. He has spent over two years harvesting and verifying femicide case data from news sources, court records and community documentation — building the verified case database at the heart of the platform.

7.  CONCLUSION AND CALL TO ACTION

FemSaidia Kenya is not a proposal. It is a live platform with six deployed tools, a working USSD shortcode, a live push notification emergency dispatch system, and a growing case database. Development risk is zero. The ask is for operational funding to make it sustainable, scalable and properly staffed.

The platform is uniquely positioned to deliver against GBV programme indicators for government, UN agencies and donors simultaneously. It is locally owned, locally built, and rooted in documented Kenyan femicide data. It reaches women on smartphones and basic phones, in cities and rural areas, with and without internet.

We invite prospective partners to visit femsaidiakenya.org, install hepa at hepa.femsaidiakenya.org, and dial *384*89056# to experience the tools firsthand. We are available for briefings, site visits and partnership discussions at any time.

Victor Ombonya · Executive Director & Lead Developer Community Media Trust · Nairobi, Kenya femsaidiakenya.org · hepa.femsaidiakenya.org · *384*89056#